## Status Report
Project Name | Simple Dungeon Crawler |  | Date |  | 2024-11-09 | Project Manager |  | Takun Purba
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Create a simple dungeon crawler game that supports local split screen co-op. |  |  |  | Determine Project Requirements |  | 100% | Complete |  | 2024-09-23
|  |  |  | Create a level |  | 0% | Future Task
|  |  |  | Create a playable character |  | 10% | Future Task
|  |  |  | Create enemies |  | 10% | Future Task
|  |  |  | Add sound effects |  | 10% | Future Task
|  |  |  | Add multiplayer functionality |  | 0% | Future Task
|  |  |  | Add models to the game |  | 10% | Future Task
|  |  |  | Full test |  | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
So far we have completed determining project requirements as a group and have assigned roles to each member as well as jobs/tasks that we will need to acommplish. | [5 empty] | Quinn- Research/sounds/recording theme. Tyler Timothy- Character Programming in Unreal. Tyler Porter- createing assets for Unreal. Jake Hunter-settting up Unreal Engine 5. Takun Purba-building AI tree
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Tyler Porter | Chief Architect | 6 | Risk | Version control on unreal engine 5 is a bit diffucult as it is possible for blueprint files to corrupt when multiple users open the same file. Another risk we run into is the individual tasks that we have will not mesh together well in the end.
Tyler Timothy | Principal Character Dynamics Specialist | 5
Quinn Barret | Audio Experience Engineer | 4
Jake Hunter | Rewards, Testing, Analysis Contractor | 4 | Issue | .Currently no issues are seen. This will be further updated as the weeks go on.
TakunPurba | Project Manager/Enemy AI | 7
Total |  | 26

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task